## Ibanda DLG 2019-20 Proc plan
PROCUREMENT PLAN FOR GOODS, WORKS AND NON-CONSULTANCY SERVICES
| Name of Procuring Entity: |  | IBANDA DISTRICT LOCAL GOVERNMENT
| Financial Year: | 2019/2020
S/No. | Subject of Procurement |  | Plan vs. Actual | [6 empty] | Invitation for Bids and Evaluation |  |  |  |  | Contract Finalization
[10 empty] | Invitation for Bidding |  | Bid Evaluation and Contract Award
|  | DEPARTMENT |  | Estimated Cost (UGX) | Source of Funding | procurement type | procurement method | contract type | prequalification ( yes/ No) | Bid Invitation Date | Bid Closing-Opening | Submission Bid Evaluation Report | Approval by CC | Award Notification Date | Contract Signature Date | Completion Date
1 | supply of fuel and lubricants for mechanised road maintenance | works | Plan | 93,967,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
2 | supply of assorted stationery | works | Plan | 5,155,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
3 | supply and installation of culverts | works | Plan | 38,000,000= | GOU | WORKS | SELECTIVE BIDDING | admeasurement | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
4 | supply of gravel | works | Plan | 39,765,000= | GOU | SUPPLIES | DIRECT PROC'T | lumpsum | no | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
5 | supply of computer and ICT supplies | works | Plan | 3,600,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
6 | supply of tyres | works | Plan | 63,713,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
7 | supply of road workers' safety ware | works | Plan | 3,186,000= | GOU | SUPPLIES | DIRECT PROC'T | lumpsum | no | N/A | N/A | N/A | N/A | N/A | N/A | 2020-06-30
Actual
8 | Building and compound maintenace | works | Plan | 8,700,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
9 | Maintenance of vehicles | works | plan | 15,900,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
10 | supply of water quality testing chemicals | Water | plan | 5,700,000= | GOU | SUPPLIES | DIRECT PROC'T | lumpsum | no | N/A | N/A | N/A | N/A | N/A | N/A | 2020-03-30
Actual
11 | construction of a 4 stance latrine with a urinal in Rukiiri S/County | Water | plan | 37,800,000= | GOU | WORKS | SELECTIVE BIDDING | admeasurement | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
12 | supply of fuel and lubricants | Water | plan | 10,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
13 | supply of stationery | water | plan | 2,076,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
14 | welfare and entertainment | Water | plan | 1,000,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
15 | Siting and Drilling of a production well in Kijongo Sub county | Water | plan | 46,500,000= | GOU | WORKS | SELECTIVE BIDDING | lumpsum | YES | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Atual
16 | Design of a piped water system in Kijongo sub county | water | plan | 27,000,000= | GOU | WORKS | SELECTIVE BIDDING | lumpsum | YES | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
17 | completion of maternity ward at Ishongororo Health centre IV | Health | plan | 54,800,000= | GOU | WORKS | OPEN BIDDING | admeasurement | No | 2019-07-15 | 2019-08-05 | 2019-08-08 | 2019-08-09 | 2019-08-26 | 2019-08-30 | 30-Feb-20
Actual
18 | supply of fuel and lubrica nts | Health | plan | 37,300,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
19 | supply of assorted stationery and office equipment | Health | Plan | 6,720,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
20 | construction of 2 satnce pit latrine at Kigunga Health centre II | Health | Plan | 12,000,000= | GOU | Works | SELECTIVE BIDDING | admeasurement | Yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
21 | repair and servicing of motorvehiles | Health | Plan | 1,600,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
22 | conference hall Hire | Health | Plan | 2,250,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
23 | construction of a 2 classroom block with an office at Rwomuhoro P/S | Education | Plan | 80,000,000= | GOU | Works | OPEN BIDDING | admeasurement | no | 2019-07-15 | 2019-08-05 | 2019-08-08 | 2019-08-09 | 2019-08-26 | 2019-08-30 | 30-Feb-20
Actual
24 | construction of a 2 classroom block with an office at Mushunga P/S | Education | Plan | 80,000,000= | GOU | Works | OPEN BIDDING | admeasurement | no | 2019-07-15 | 2019-08-05 | 2019-08-08 | 2019-08-09 | 2019-08-26 | 2019-08-30 | 30-Feb-20
Actual
25 | construction of a 2 classroom block with an office at Kanoni ii Primary School in Rukiiri S/C | Education | Plan | 80,000,000= | GOU | WORKS | OPEN BIDDING | admeasurement | no | 2019-07-15 | 2019-08-05 | 2019-08-08 | 2019-08-09 | 2019-08-26 | 2019-08-30 | 30-Feb-20
Actual
26 | construction of a 2 classroom block with an office at Rwemirama Primary school in Nyamarebe S/C | Education | plan | 80,000,000= | GOU | WORKS | OPEN BIDDING | admeasurement | no | 2019-07-15 | 2019-08-05 | 2019-08-08 | 2019-08-09 | 2019-08-26 | 2019-08-30 | 30-Feb-20
Actual
27 | construction of a 5 stance lined latrine at Rwenkuba P/S in Kikyenkye Sub county | Education | plan | 30,000,000= | GOU | WORKS | SELECTIVE BIDDING | admeasurement | no | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
28 | printing and supply of Mock and P 6 End of year exams | Education | Plan | 10,000,000= | GOU | SUPPLIES | OPEN BIDDING | lumpsum | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
29 | supply of fuel and lubricants | Education | Plan | 30,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
30 | supply of assorted stationery | Education | Plan | 5,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
31 | motorvehicle repairs and tyres | Education | plan | 9,400,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
32 | supply of fuel and lubricants | Finance | plan | 6,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
33 | supply of assorted and printed stationery and small office equipment | Finance | Plan | 16,800,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
34 | computer servicing and engravement | Finance | Plan | 1,000,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
35 | sourcing of providers for collection of revenue from markets | Finance | Plan | 500,000,000= | N/A | SERVICES | OPEN BIDDING | Lumpsum | no | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
36 | Generator servicing | Finance | Plan | 6,200,000= | GOU | Works | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
37 | supply of meals and refreshments | Finance | Plan | 2,000,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
38 | purchase of airtime | Finance | plan | 2,000,000= | GOU | SUPPLIES | MICRO PROC'T | lumpsum
Actual
39 | supply of male boer Goats | Production | Plan | 20,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
40 | supply of banana suckers | Production | Plan | 10,000,000= | GOU | Works | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
41 | supply of pasture seeds | Production | Plan | 2,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
42 | supply of irrigation kits and establishment of rain water harvesting tanks | Production | Plan | 40,249,560= | GOU | SUPPLIES | OPEN BIDDING | lumpsum |  | 2019-07-15 | 2019-08-05 | 2019-08-08 | 2019-08-09 | 2019-08-26 | 2019-08-30 | 30-Feb-2020
Actual
43 | establishment of apiary demo and honey harvesting kits | Production | Plan | 4,000,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
44 | supply of Fish fry and fish feeds | Production | Plan | 44,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
45 | supply of fuel and lubricants | Production | Plan | 97,348,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
46 | supply of assorted stationery,and photocopying services | Production | Plan | 7,334,464= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
47 | supply of field tools and equipment | Production | Plan | 6,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
48 | purchase of airtime | Production | Plan | 6,000,000= | GOU | SUPPLIES | MICRO PROC'T | lumpsum | yes | N/A | N/A | N/A | N/A | N/A | N/A | 2020-06-30
Actual
49 | Maintenance and repair of motor cycles | CBS | Plan | 2,400,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
50 | supply of office shelves,carpets and cupboards | CBS | Plan | 400,000= | GOU | SUPPLIES | MICRO PROC'T | lumpsum | NO | N/A | N/A | N/A | N/A | N/A | N/A | 2020-06-30
Actual
51 | supply of computer and ICT accessories | CBS | Plan | 6,000,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
52 | supply of meals and refreshments | CBS | Plan | 3,600,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual | bar: 2019-05-10 to 2019-06-28
53 | supply of a water dispenser, mineral water and disposables | CBS | Plan | 1,450,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
54 | supply of office stationery, cleaning materials and other small office equipment | CBS | plan | 2,450,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | YES | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
55 | Supply of fuel | CBS | plan | 4,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
56 | supply of assistive devices for PWDS | CBS | plan | 600,000= | GOU | SUPPLIES | DIRECT PROC'T | Lumpsum | no | N/A | N/A | N/A | N/A | N/A | N/A | 2020-06-30
Actual
57 | supply o office stationery | INTERNAL AUDIT | Plan | 600,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
58 | supply of fuel and lubricants | INTERNAL AUDIT | Plan | 3,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
59 | supply of corporate wear | INTERNAL AUDIT | Plan | 200,000= | GOU | SUPPLIES | MICRO PROC'T | lumpsum | no | N/A | N/A | N/A | N/A | N/A | N/A | 2019-06-30
actual
60 | supply of a photocopier | PROCUREMENT | Plan | 3,500,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | YES | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2019-10-30
Actual
61 | supply of assorted stationery | PROCUREMENT | Plan | 3,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
62 | supply of fuel | NATURAL RESOURCES | Plan | 800,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
63 | supply of assorted stationery | NATURAL RESOURCES | Plan | 1,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
64 | computer Maintenance | NATURAL RESOURCES | Plan | 1,000,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
65 | supply of office stationery | PLANNING UNIT | Plan | 4,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
66 | supply of fuel | PLANNING UNIT | Plan | 6,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
67 | repair and maintenance of computer | PLANNING UNIT | Plan | 500,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
68 | supply of computers and ICT equipment | PLANNING UNIT | Plan | 3,378,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2019-05-01 | 2019-05-22 | 2019-05-24 | 2019-05-27 | 2019-06-10 | 2019-06-13 | 2020-06-30
Actual
69 | welfare and entertainment incuding meal | PLANNING UNIT | Plan | 4,800,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
70 | Supply of fuel | ISHONGORORO T/C | Plan | 35,494,800= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
71 | Supply and installation of Culverts | ISHONGORORO T/C | Plan | 11,600,000= | GOU | Works | SELECTIVE BIDDING | lumpsum | YES | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
actual
72 | Installation of solar powered street lights | ISHONGORORO T/C | plan | 20,000,000= | GOU | Works | SELECTIVE BIDDING | admeasurement | YES | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
73 | supply of fuel and lubricants | RWENKOBWA TOWN COUNCIL | Plan | 23,390,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
actual
74 | Supply and installation of Culverts | RWENKOBWA TOWN COUNCIL |  | 12,258,000= | GOU | Works | SELECTIVE BIDDING | admeasurement | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
75 | Installation of hydro electricity power to town council offices | RWENKOBWA TOWN COUNCIL | Plan | 900,000= | GOU | Works | DIRECT PROC'T | lumpsum | NO | N/A | N/A | N/A | N/A | N/A | N/A | 2020-06-30
actual
76 | Suppl of stationery | RWENKOBWA TOWN COUNCIL | Plan | 2,500,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
actual
77 | purchase of land for the playground | RUSHANGO TOWN COUNCIL | Plan | 6,600,000= | GOU | Works | OPEN BIDDING | Lumpsum | No | 2019-07-15 | 2019-08-05 | 2019-08-08 | 2019-08-09 | 2019-08-26 | 2019-08-30 | 30-Feb-2020
Actual
78 | Supplyof fuel and lubricants | RUSHANGO TOWN COUNCIL | Plan | 22,500,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
79 | Supply and installation of Culverts | RUSHANGO TOWN COUNCIL | plan | 16,950,000= | GOU | SUPPLIES | SELECTIVE BIDDING | admeasurement | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
80 | Cutting Edges | RUSHANGO TOWN COUNCIL | Plan | 6,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
Actual
81 | Murram/Gravel | RUSHANGO TOWN COUNCIL | plan | 15,750,000= | GOU | SUPPLIES | OPEN BIDDING | lumpsum | yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
actual
82 | Stationery | RUSHANGO TOWN COUNCIL | Plan | 1,500,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
actual
83 | Supply of office furniture | RUSHANGO TOWN COUNCIL | Plan | 3,000,000= | GOU | SUPPLIES | SELECTIVE BIDDING | Lumpsum | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
actual
84 | Supply of twin desks for schools | Nyamarebe sub county | Plan | 16,000,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
actual
85 | Completion of a production Hall | KICUZI SUB COUNTY | Plan | 7,000,000= | GOU | Works | SELECTIVE BIDDING | lumpsum | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
actual
86 | Supply of 3 seater twin desks for schools of Mushunga, Kashozi, katengyeto and Muziza | ISHONGORORO SUB-COUNTY | Plan | 8,700,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
actual
87 | Supply 3 seater twin desks for schools | KEIHANGARA SUB-COUNTY | Plan | 6,890,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
actual
88 | Completion of a latrine in Kikyenkye Subcounty | KIKYENKYE SUB-COUNTY | Plan | 7,000,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
89 | Supply 3 seater twin desksto kakindo P/s | KIJONGO SUB-COUNTY | Plan | 7,600,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
90 | Construction of a slaughter slab | IGORORO TOWN COUNCIL | Plan | 8,515,292= | GOU | Works | SELECTIVE BIDDING | admeasurement | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
Actual
91 | Fuel, oil and Lubricants | IGORORO TOWN COUNCIL | Plan | 24,228,160= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
actual
92 | Supply and installation of Culverts | IGORORO TOWN COUNCIL | Plan | 8,540,000= | GOU | Works | SELECTIVE BIDDING | admeasurement | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
actual
93 | Supply of stationery both assorted and printed | IGORORO TOWN COUNCIL | Plan | 3,300,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
actual
94 | Installation of solar powered street lights | IGORORO TOWN COUNCIL | Plan | 11,250,000= | GOU | Works | SELECTIVE BIDDING | lumpsum | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
actual
95 | Supply of cutting edges | IGORORO TOWN COUNCIL | Plan | 4,884,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 2019-05-10 | 2019-05-31 | 2019-06-05 | 2019-06-10 | 2019-06-24 | 2019-06-28 | 2020-06-30
actual
96 | Supply of computer laptop and ICT supplies | IGORORO TOWN COUNCIL | Plan | 4,600,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
actual
97 | Supply of Tree seedlings | IGORORO TOWN COUNCIL | Plan | 220,000= | GOU | SUPPLIES | DIRECT PROC'T | lumpsum | NO | N/A | N/A | N/A | N/A | N/A | N/A | 2019-06-30
actual
98 | construction of a 2 stance pit latrine in Nyabuhikye sub county | Nyabuhikye sub county | plan | 9,800,000= | GOU | Works | SELECTIVE BIDDING | admeasurement | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
actual
99 | construction of a 3 stance pit latrine at Rwijogoro Primay School | Rukiiri subcounty | plan | 15,230,000= | GOU | Works | SELECTIVE BIDDING | admeasurement | yes | 2019-08-12 | 2019-08-26 | 2019-08-29 | 2019-08-30 | 2019-09-16 | 2019-09-20 | 2020-03-20
actual
| Prepared by | Name: |  | Albus Tumwekwatse
Signature:
|  | Position: |  | Senior Procurement Officer
Date:
| Approved by | Name: |  | AHIMBISIBWE NATHAN
Signature:
|  | Position: |  | CHIEF ADMINISTRATIVE OFFICER
Date:

## Consultancy
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - FOR SUBMISSION TO THE SECRETARY TO TREASURY, PPDA AND PUBLICATION
Procuring and Disposing Entity:
Financial Year:
S/No | Subject of procurement | Plan vs. Actual | Estimated cost and currency | Source of funding | Procurement method | Contract type | Request for Expression of Interest |  |  |  | Invitation of proposals and approval for award |  |  |  |  | Completion date
[7 empty] | Invitation of Expressions of Interest date | Closing-Opening date | Approval of shortlist | Notification date | Invitation of proposals date | Submission/ opening date | Approval of final evaluation report | Notification date | Contract signing date
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
| Prepared by |  | Name: |  |  |  | Approved by | Name
|  |  | Signature: |  |  |  |  | Signature:
|  |  | Designation: |  |  |  |  | Designation:
|  |  | Date: |  |  |  |  | Date:

## Consultancy - Internal use
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - INTERNAL USE
Name of the Procuring Entity:
Financial Year:
S/No. | Subject of Procurement | Plan vs. Actual | Basic Data |  |  |  | Request for Expression of Interest |  |  |  | Preparation of RFP Documents |  | Invitation of proposals and approval for award | [6 empty] | Contract Finalization
|  |  | Estimated Cost and Currency | Procurement Method | Selection Method | Contract Type | Invitation |  | Evaluation |  |  |  | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F)
[7 empty] | Invitation Date | Closing-Opening | Submission Evaluation Report | Approval of Shortlist | Prep & Submission by PDU | Approval by CC | Invitation Date | Submission/ Opening Date | Submission Evaluation Report | Approval of Technical Evaluation Report. | Opening Financial Proposals | Submission of Final Evaluation Report | Approval EvaluationReport | Contract Value | Contract Award Date | Contract Signature Date
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
| Total Cost | Plan
Actual
| Prepared by |  | Name:
Signature:
Designation:
Date:
| Approved by |  | Name:
Signature:
Designation:
Date: